NMIMS MPSTME / NMIMS HYDERABAD • DEPARTMENT OF COMPUTER ENGINEERING

CAPSTONE PROJECT STATUS REPORT

Vision Error Observatory (VEO) — Comprehensive Diagnostic Workstation for Monocular Depth Estimation

| Project Title: Vision Error Observatory (VEO) | Academic Year / Term: 2026–2027 (Final Year B.Tech) |
| --- | --- |
| Lifecycle Phase: Execution & Pre-Closure (Sprint 5–6) | PM Methodology: Hybrid (Agile Sprints + Stage-Gate) |
| Reporting Date: October 27, 2026 | Target Audience: Project Management & Technical Advisory Faculty |

1.0 EXECUTIVE SUMMARY & TRIPLE CONSTRAINT HEALTH (RAG STATUS)

The Vision Error Observatory (VEO) project evaluates where, how, and why monocular depth estimation models fail. Unlike standard black-box evaluation, VEO introduces an explainable, post-hoc diagnostic framework combining quantitative error localization, a multi-factor failure taxonomy, and an interactive 3D WebGL observatory. Current overall project health is Green, with core pipeline modules, 1,449 NYU benchmark runs, and the complete academic manuscript achieved on schedule.

| Constraint / Pillar | RAG Status | Trend | Executive Assessment & Variance |
| --- | --- | --- | --- |
| Overall Project Health | ● GREEN | ↗ Improving | Core pipeline, dataset evaluations, academic paper, and web app fully operational. |
| Scope Baseline | ● GREEN | → Stable | Frozen to indoor NYU Depth V2 and Hypersim. Out-of-scope items (KITTI) excluded via change control. |
| Schedule (Time) | ● GREEN | ↗ Ahead | SPI = 1.04. Sprints 1–5 completed 4 days ahead of baseline critical path. |
| Cost & Resources | ● GREEN | → Controlled | CPI = 1.00. Zero cloud debt; 100% open-source local inference and offline WebGL visualization. |
| Quality & Governance | ● GREEN | → Stable | 100% test pass rate across 11 system endpoints; mathematical validation on depth metrics. |

2.0 PROJECT CHARTER & SCOPE TRACEABILITY

Scope Baseline & Governance: To prevent scope creep while fulfilling rigorous academic research standards, boundaries were formalized during Sprint 1. The project does not train new foundational models from scratch; instead, it establishes an interpretable, post-hoc diagnostic observer.

In-Scope Deliverables (Verified): Full dataset ingestion & calibration for NYU Depth V2 (1,449 images); Depth Anything V2 (ViT-Small) and Intel DPT-Hybrid model benchmarking; arbitrary 5×5 pixel region selection; multi-hypothesis causal taxonomy scoring (Textureless, Specular, Depth Discontinuity, Vignetting); offline, zero-CORS 3D WebGL interactive observatory; full IEEE-compliant academic manuscript.

Out-of-Scope Exclusions (Controlled): Outdoor automotive datasets (KITTI) excluded due to sparse LiDAR point cloud artifacts violating indoor continuous surface assumptions; end-to-end retraining of multi-million parameter vision transformers (unnecessary for diagnostic explainability research).

3.0 WORK BREAKDOWN STRUCTURE (WBS) & DELIVERABLES TRACKER

The project execution is organized across 5 distinct work packages (WBS 1.0 to WBS 5.0). Each work package maps to concrete verification artifacts within the repository.

| WBS | Deliverable Name | Planned | Actual | Status | Verification Evidence |
| --- | --- | --- | --- | --- | --- |
| 1.3 | Depth Calibration Suite | Week 3 | Week 3 | 100% Done | scripts/test_uint16_depth.py |
| 2.4 | Causal Taxonomy Classifier | Week 5 | Week 5 | 100% Done | outputs/nyu_final/test/summary.json |
| 3.1 | NYU Depth V2 Benchmark | Week 7 | Week 6 | 100% Done | 1,449 samples evaluated; official metrics |
| 3.2 | Multi-Model Comparison | Week 8 | Week 8 | 100% Done | Intel/dpt-hybrid-midas benchmarked |
| 3.3 | Threshold Ablation Study | Week 8 | Week 8 | 100% Done | 75th, 85th, 90th, 95th percentiles |
| 4.4 | 3D Interactive Web App | Week 9 | Week 9 | 100% Done | http://localhost:8000/index.html |
| 5.2 | Conference Paper Manuscript | Week 10 | Week 9 | 100% Done | VEO_conference_paper_final.pdf (IEEE) |

4.0 SCHEDULE PERFORMANCE & CRITICAL PATH ANALYSIS

Project execution followed an Agile-Stage Gate model with 2-week sprint cycles. The project critical path consisted of 5 zero-float sequential milestones:

Milestone M1 (Sprint 1, Wk 2): Scope & Sensor Calibration Baselined — [COMPLETED (On Schedule)]

Milestone M2 (Sprint 2, Wk 4): Error Extraction & Heuristic Taxonomy Validated — [COMPLETED (On Schedule)]

Milestone M3 (Sprint 3, Wk 6): 1,449 NYU Benchmark & Comparative Model Evaluated — [COMPLETED (1 Wk Ahead)]

Milestone M4 (Sprint 4, Wk 8): 3D Interactive Exhibition Web Observatory Operational — [COMPLETED (On Schedule)]

Milestone M5 (Sprint 5, Wk 10): Academic Manuscript & Capstone Defense Package — [ACTIVE (90% Ready)]

Earned Value & Schedule Variance Indicators:
• Schedule Performance Index (SPI): 1.04 (SPI > 1.0 indicates project delivery velocity exceeds planned schedule baseline).
• Schedule Variance (SV): +4 Days (Ahead of critical path milestones).
• Critical Path Integrity: Zero blocked tasks on critical path; all downstream thesis writing dependencies cleared.

5.0 RAID LOG (RISKS, ASSUMPTIONS, ISSUES, DEPENDENCIES)

Formal risk management was conducted dynamically throughout development to eliminate technical and evaluator evaluation blockers.

| ID | Category | Risk Description | Severity | Likelihood | Mitigation & Action Taken |
| --- | --- | --- | --- | --- | --- |
| R-01 | Evaluator | Faculty reviewers find complex depth math opaque or hard to judge. | HIGH | HIGH | Built an 8-scene 3D interactive web observatory. Allows live crosshair inspection and 3D error stem visualization. |
| R-02 | Technical | Live GPU / PyTorch dependency failure during live defense demonstration. | HIGH | LOW | Pre-computed 9.2 MB zero-latency data payload (app_data_v2.js). Runs offline with zero external cloud or GPU dependency. |
| R-03 | Validation | Subjectivity in rule-based failure taxonomy classification. | MED | MED | Implemented blinded rating package export with Cohen's Kappa inter-rater agreement validation protocol. |

6.0 QUALITY ASSURANCE (QA) & KEY PERFORMANCE INDICATORS (KPIS)

| Key Performance Indicator (KPI) | Target Baseline | Achieved Metric | Compliance |
| --- | --- | --- | --- |
| Automated Server Endpoint Health | 100% Pass | 11/11 endpoints returning HTTP 200 | MET (100%) |
| Depth Anything V2 NYU Error (AbsRel) | < 0.100 | 0.086 (Exceeds baseline threshold) | MET (Exceeded) |
| Diagnostic Processing Throughput | < 1.00 s/image | 0.28 s/image (Optimized numpy/torch) | MET (Exceeded) |
| Interactive WebGL Rendering Frame Rate | ≥ 30 FPS | 60 FPS (Zero stutter, client-side Three.js) | MET (Exceeded) |
| Zero-Dependency Architecture (Offline Portability) | 100% Offline | Self-contained CSS & assets (Zero CDN failure) | MET (100%) |

7.0 RESOURCE & BUDGET UTILIZATION

• Financial Budget: ₹0.00 Expended / ₹0.00 Allocated. Variance = 0. Zero external subscription or cloud provider costs.
• Infrastructure & Compute: Local workstation equipped with NVIDIA RTX GPU for model activation extraction. Production deployment utilizes optimized browser WebGL, requiring no ongoing server compute spend.
• Open Source Assets: Depth Anything V2, Intel DPT-Hybrid, Three.js (r128), Chart.js, FontAwesome (all locally mirrored in /web_app/assets/).

8.0 SPRINT LOOKAHEAD & FINAL CAPSTONE DEFENSE READINESS

• Sprint 7 (Current Sprint - Week 11): Finalize blinded human-in-the-loop rater verification; compute multi-rater Cohen's Kappa score.
• Sprint 8 (Final Sprint - Week 12): Conduct Capstone Oral Defense dry-run with project advisor using the interactive web observatory. Finalize institutional repository archive and formal thesis submission.